## Sheet1
DEFAULT COMPANY GANTT CHART
TASKS | Predicted | Hours Spent | Previous Task | Current Status: | COMPLETE |  | IN PROGRESS |  |  | SLACK |  | PLANNED
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
JOSH: TEAM LEAD #1 |  |  |  | PLANNED
1. REQUIREMENT GATHERING | 5 |  | START | PLANNED | COMPLETE 1: start
2. DESIGN BOSSES | 10 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 15
3. IMPLEMENT BOSSES | 20 |  | 2 | PLANNED | PLANNED 16: 2
4. TEST FUNCTION OF ENCOUNTERS | 5 |  | 3 | PLANNED | PLANNED 36: 3
5. REBALANCE ENCOUNTERS | 5 |  | 4 | PLANNED | PLANNED 41: 4
6. AQUIRE ART ASSETS | 5 |  | 2 | PLANNED | PLANNED 16: 2
7. FINAL PLAY TEST AND REBALANCE | 5 |  | 5 | PLANNED | PLANNED 21: 5
8. DOCUMENTATION | 2 |  | 3 | PLANNED | PLANNED 36: 3
9.INSTALATION | 1 |  | 6,7,8 | PLANNED | PLANNED 38: 6,7,8
TOTAL HOURS PLANNED: 58 | TOTAL HOURS ACTUAL: 0
TASKS | Predicted | Hours Spent | Previous Task | Current Status: | COMPLETE 1: COMPLETE; IN PROGRESS 3: IN PROGRESS; SLACK 6: SLACK; PLANNED 8: PLANNED
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
JACOB: TEAM LEAD #2 |  |  |  | PLANNED
1. DESIGN ALL ROOMS | 24 |  | START | PLANNED | COMPLETE 1: start
2. ROOM DATABASE CONSTRUCTION | 5 |  | 1 | PLANNED | bar: PLANNED 25 to PLANNED 29
3. USER DOCUMENTATION | 3 |  | 2 | PLANNED | PLANNED 30: 2
4. PROGRAMMING | 15 |  | 3 | PLANNED | PLANNED 33: 3
5. TESTING | 5 |  | 4 | PLANNED | PLANNED 48: 4
6. INSTALLATION | 5 |  | 5 | PLANNED | PLANNED 53: 5
TOTAL HOURS PLANNED: 57 | TOTAL HOURS ACTUAL: 0
TASKS | Predicted | Hours Spent | Previous Task | Current Status: | COMPLETE 1: COMPLETE; IN PROGRESS 3: IN PROGRESS; SLACK 6: SLACK; PLANNED 8: PLANNED
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
BEN: TEAM LEAD #4
1. REQUIREMENT GATHERING | 5 |  | START | COMPLETE | COMPLETE 1: start
2. ITEM CLASS DESIGN | 10 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 15
3. ITEM POOL IMPLEMENTATION | 6 |  | 2 | PLANNED | PLANNED 16: 2
4. ITEM AVAILABLE SLOT DESIGN | 4 |  | 3 | PLANNED | PLANNED 22: 3
5. ITEM SPRITE IMPLEMENTATION | 5 |  | 4 | PLANNED | PLANNED 26: 4
6. AUDIO IMPLEMENTATION | 5 |  | 4 | PLANNED | PLANNED 26: 4
7. INTEGRATING DESIGN | 10 |  | 5,6 | PLANNED | PLANNED 31: 5,6
8. TESTING | 8 |  | 7 | PLANNED | PLANNED 41: 7
9.INSTALATION | 3 |  | 8 | PLANNED | PLANNED 49: 8
TOTAL HOURS PLANNED: 56 | TOTAL HOURS ACTUAL: 0
TASKS | Predicted | Hours Spent | Previous Task | Current Status: | COMPLETE 1: COMPLETE; IN PROGRESS 3: IN PROGRESS; SLACK 6: SLACK; PLANNED 8: PLANNED
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
RYAN: TEAM LEAD #5 |  |  |  | PLANNED
1. REQUIREMENT GATHERING | 5 |  | START | PLANNED | COMPLETE 1: start
2. ENEMY TYPE PROGRAMMING | 7 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 12
3. ENEMY MOVEMENT PROGRAM | 7 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 12
4. COLLISION PROGRAMMING | 5 |  | 2,3 | PLANNED | PLANNED 13: 2,3
5. SPRITE ANIMATION/SOUND | 6 |  | 2 | PLANNED | PLANNED 13: 2
6. DOCUMENTATION | 5 |  | 4,5 | PLANNED | PLANNED 19: 4,5
7. TESTING | 5 |  | 4,5 | PLANNED | PLANNED 19: 4,5
8. INSTALATION | 5 |  | 7 | PLANNED | PLANNED 24: 7
TOTAL HOURS PLANNED: 45 | TOTAL HOURS ACTUAL: 0
TASKS | Predicted | Hours Spent | Previous Task | Current Status: | COMPLETE 1: COMPLETE; IN PROGRESS 3: IN PROGRESS; SLACK 6: SLACK; PLANNED 8: PLANNED
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
CHRIS: TEAM LEAD #6 |  |  |  | PLANNED
1. REQUIREMENT GATHERING | 5 |  | START | PLANNED | COMPLETE 1: start
2. PLAYER MOVEMENT PROGRAM | 5 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 10
3. PLAYER ATTACKING PROGRAM | 5 |  | 1 | PLANNED | bar: SLACK 6 to PLANNED 10
4. COLLISION PROGRAMMING | 4 |  | 2 | PLANNED | PLANNED 11: 2
5. HAZARD DESIGN/PROGRAM | 6 |  | 2 | PLANNED | PLANNED 11: 2
6. PLAYER CLASS DESIGN/PROGRAM | 6 |  | 2,3 | PLANNED | PLANNED 11: 2,3
7. DOCUMENTATION | 5 |  | 6 | PLANNED | PLANNED 16: 6
8. TESTING | 5 |  | 6 | PLANNED | PLANNED 16: 6
9. INSTALATION | 5 |  | 6 | PLANNED | PLANNED 16: 6
10. ARTWORK/SOUND | 6 |  | 2,3 | PLANNED | PLANNED 11: 2,3
TOTAL HOURS PLANNED: 52 | TOTAL HOURS ACTUAL: 0